## UAT1
No. | Area | Details | Developer Comments
1 | Welcome Page | Lefthand margin needs 0.5cm edge, particularly evident in Mobile view.
2 | Welcome Page | Can the Portal link wording be slightly larger?
3 | Moto | Should read in one line as: "Stone Signs: Providing a rock-solid service". I can recall where I saw it two line now, other than the reset email, see point below.
4 | Password reset email | Refer to Password Reset Email tab.
5 | List View | Wrap all Date/Time columns so Date is on Line 1 and Time is on Line 2, making column width smaller.
6 | List View | Preferred Column order: 1. Branch 2. Sign 3. Address 4. Status 5. Controls 6. Original Request Date/Time (see point below) 7. Completed Date/Time 8. Updated Date/Time??
7 | List View, Request Date field | This should not update if Ben makes an amendment to the request, as we need to know when the Agent made their Original Request.
8 | List View, Date/Time field | Date/Time fields not displaying correctly. Showing as: NaN/NaN/NaN:NaN:NaN. Possibly only this particular iPad affected?
9 | List view, Control icons | Please enlarge control icons
10 | Agents & Branches | How do we delete an Agent or Branch?
11 | Agents & Branches, Branch logins | How can I review the Branch logins set-up? We need visibility of this.
12 | Agents & Branches, Naming convention | Format will be Agent@Location, so no need for Agent in the List view.
13 | Agents & Branches, Sign Pricing label | Please rename Replace to Re-erect in Agent Pricing.
14 | Last View | Return to last view, rather than default page. E.g. When viewing list view, do not return to Map view. Also when viewing list and marking as complete, return to same row rather than jump to the top of the list view.
15 | Last Map View | Whenever a request is confirmed, the map re-centralises. It is possible to have the map return to last viewed area. Particularly important if marking 6 signs in one areas as complete. Currently User keeps having to re-scale.
16 | Form Completion, No. of Signs | This should be zero for a blank form and a mandatory field.
17 | Form Completion, Save button | Please rename to Submit.
18 | Form completion | After saving form request, it would feel better to close form and return to higher level screen. This would also work well when saving Agent & Branch information.
19 | Form Completion | Scenario: Agent requested For Sale, Ben marked as complete, Agent went to change sign but changed from Sales to Letting, and this was allowed to be processed by the app. Sign Categories (Sales, Letting Sponsorship, Commercial) should not be allowed to be amended, once in play.
20 | Form Completion, Sponsorship Form, Location field | What is the Location field for?
21 | Pop-up windows | Would it be possible to have the Save and Close near top of window as this is easier with mobile and tablet views.
22 | Requests, deleting requests | If agent makes a request for 2 signs, and then decided to delete, they are required to delete twice.
23 | Parent-Child | Identify Parent request, so if all signs are placed, can tick just Parent. If not all signs placed, can mark each as appropriate. E.g. 2 signs requested, sign at front successful, sign at back not successful. Suggestion: Have child actions in dark grey font colour instead of the usual black.
24 | Parent & Child entries | Request for 22 Commercial signs, showing as 22 individual entries in spreadsheet. However for Sponsorship, one entry shown with x Quantity requested. Is it possible to have the latter format for Commercial signs, particularly in the case of Invoicing when one entry is preferred. Invoice Example shown on Invoice tab.
25 | Status labels | Requests Made=Pending Not Invoice, please rename in both areas to Pending. Areas are: - List View, - Status Filter
26 | Status Filters Groupings | Completed (Not Invoiced) and Unsuccessful (Not Invoiced) should appear in an additional Not Invoiced filter for Invoicing.
27 | Status labels, Invoicing | Once invoiced, the Completed or Unsuccessful is no longer visible. So from the Agent perspective, when filtering by Unsuccessful, although the results are true, the labels aren't visible. Agent filter options are: Pending, Completed & Unsuccessful. This information is available as part of the CSV export, Columns N & O. Not sure on solution here.
28 | Invoicing | Is it possible to have the file name as a heading in the CSV? See screen snip:

## Password Reset Email
Before:
Please change to:

## Invoice
Request Date | Charge Date | Request Description | Address | Status | Cost
2019-11-30 21:22 | 2019-11-30 22:38 | Sales, New Sign, Under Offer | 1 Adversane road, Worthing, BN14 7QH | Completed | 20
2019-11-30 21:22 | 2019-11-30 22:38 | Sales, New Sign, Under Offer | 1 Adversane road, Worthing, BN14 7QH | Completed | 20
2019-11-28 19:21 | 2019-11-29 14:20 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:26 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:01 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:03 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:05 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:05 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-30 19:35 | 2019-11-30 20:34 | Sales, New Sign, Under Offer | 130 Terringes Avenue, Worthing, BN13 1JP | Completed | 20
2019-11-30 19:46 | 2019-11-30 20:09 | Commercial, New Sign, V-Board, To Let | 27a, Chapel road, Worthing, BN11 1EG | Completed | 100
2019-11-30 19:33 | 2019-11-30 20:31 | Letting, New Sign, To Let | 34 Adversane road, Worthing, BN14 7QH | Completed | 20
2019-11-30 20:42 | 2019-11-30 20:46 | Sales, New Sign, For Sale | 36 Charles Avenue, Chichester, PO19 7HF | Completed | 20
2019-11-30 19:40 | 2019-11-30 20:30 | Sales, New Sign, Sold STC | 42 Adversane road, BN14 7QH | Completed | 20
2019-11-30 19:38 | 2019-11-30 20:21 | Sponsorship, New Sign x 15 | Broadwater green, BN14 9DJ | Completed | 300
2019-11-28 19:30 | 2019-11-30 21:00 | Sponsorship, New Sign x 10 | George & Gragon, Worthing, BN14 7NN | Completed | 200