## 2019-11-30
No. | Area | Details | Developer Comments | Update 02-12-2019
1 | Welcome Page | Lefthand margin needs 0.5cm edge, particularly evident in Mobile view. | Is the intent here to keep the text area the same width as the photo? If so, not so much a case of giving it a 0.5 cm margin but more setting the display area the same width as the image width. Otherwise mobile devices with other screen sizes will still have a potential indent around the picture. | Completed
2 | Welcome Page | Can the Portal link wording be slightly larger? | This is fine, I suggest increasing it to the same size as the Privacy Policy link (increasing from 9pt to 10.5pt font size) | Completed
3 | Moto | Should read in one line as: "Stone Signs: Providing a rock-solid service". I can recall where I saw it two line now, other than the reset email, see point below. | The moto is split on two lines in all the emails. I can change this to match the site. To avoid a large blank area underneath the motto I’ll make the masthead smaller. | Completed
4 | Password reset | Refer to Password Reset Email tab. | I will take a look at the formatting. Clearly this is showing differently between mail clients. | When taken to the password reset screen, please ensure both field are blank, ready for new password to be entered.
5 | List View | Wrap all Date/Time columns so Date is on Line 1 and Time is on Line 2, making column width smaller. | Not a problem, and something I had considered myself | Completed
6 | List View | Preferred Column order: 1. Branch 2. Sign 3. Address 4. Status 5. Controls 6. Original Request Date/Time (see point below) 7. Completed Date/Time 8. Updated Date/Time?? | Not a problem to rearrange the columns. Is the Updated column to be the date / time the request was modified (considering your point below). It would require a small change to the database but could be done. | Completed
7 | List View, Request Date field | This should not update if Ben makes an amendment to the request, as we need to know when the Agent made their Original Request. | Not a problem, I can remove the part of the code that updates the date on changes. Plus reading this in conjunction with the previous point, I can add a new Updated field to store this. In the case of an agent making a change, should this follow the same rules as for Ben? For example, one Ben has placed a sign, if the agent then updates the request to a removal, should the requested date or the updated date be changed? | A removal request is a new request, and as far as I understand, will be a new entry, therefore requiring a new Original Request Date.
8 | List View, Date/Time field | Date/Time fields not displaying correctly. Showing as: NaN/NaN/NaN:NaN:NaN. Possibly only this particular iPad affected? | I will need to take a deeper look at this. Possibly a difference in iOS’s javascript handling of dates. | Resolved
9 | List view, Control icons | Please enlarge control icons | Not a problem, I had been anticipating possibly receiving this request. | Completed & much better thanks
10 | Agents & Branches | How do we delete an Agent or Branch? | We hadn’t discussed deletion. If this is a requirement, I suggest we disable them, rather than delete them, for data integrity purposes. | Agreed, will rename to e.g. zzFox & Sons.
11 | Agents & Branches, Branch logins | How can I review the Branch logins set-up? We need visibility of this. | To clarfy, you wish for the username field to be visible on the Branch editor? Should this be readonly? Presumably password should still not be available, unless you want to be able to change it? | Yes login to be read only. This means I only get one change to set-up correctly. I suppose worse case I can always rename to "not in use", and start again.
12 | Agents & Branches, Naming convention | Format will be Agent@Location, so no need for Agent in the List view. | Not a problem, I will revert the lists to the single column format. | Agent Name not rquired in List View for Admin login either.
13 | Agents & Branches, Sign Pricing label | Please rename Replace to Re-erect in Agent Pricing. | Not a problem. | Completed
14 | Last View | Return to last view, rather than default page. E.g. When viewing list view, do not return to Map view. Also when viewing list and marking as complete, return to same row rather than jump to the top of the list view. | 1) I will look into this. 2) I will see what can be done for this, I have a solution in mind. | Completed, and very pleasing.
15 | Last Map View | Whenever a request is confirmed, the map re-centralises. It is possible to have the map return to last viewed area. Particularly important if marking 6 signs in one areas as complete. Currently User keeps having to re-scale. | I may be limited in what control I have over this, however I will try to find a solution, if one is possible. | Completed, and again, very pleasing. Also agree with your point for resetting the map for Region & Branch filters but please see point 30 below regarding List View filters.
16 | Form Completion, No. of Signs | This should be zero for a blank form and a mandatory field. | Not a problem. | Completed
17 | Form Completion, Save button | Please rename to Submit. | Not a problem, do you want this renamed on admin forms as well, or just the request form? | Completed, not sure any further changes are required. TBC
18 | Form completion | After saving form request, it would feel better to close form and return to higher level screen. This would also work well when saving Agent & Branch information. | So return to the list? That’s not a problem. | Completed
19 | Form Completion | Scenario: Agent requested For Sale, Ben marked as complete, Agent went to change sign but changed from Sales to Letting, and this was allowed to be processed by the app. Sign Categories (Sales, Letting Sponsorship, Commercial) should not be allowed to be amended, once in play. | Ok, I will make this field read only when editing a sign that has been placed. | Completed
20 | Form Completion, Sponsorship Form, Location field | What is the Location field for? | This allows you to find an existing sponsorship. Essentially, since we do not have the New, Change, etc options for sponsorships, the Location field needs to be always on for modifying a sponsorship request. If you would prefer not to have this it can be removed. | I understand the use of the field now. Need to review further. Also used in other re-erect and remove forms.
21 | Pop-up windows | Would it be possible to have the Save and Close near top of window as this is easier with mobile and tablet views. | My initial feeling is that goes against common dialogue design, but perhaps smaller buttons in the top right of the pop-ups would work. I will look in to what can be done with the layout. | Completed and very pleasing.
22 | Requests, deleting requests | If agent makes a request for 2 signs, and then decided to delete, they are required to delete twice. | This ties in with your similar point below about Ben being able to mark multiple signs as completed. You already know my initial thoughts on this but I have been thinking further on the matter. Perhaps rather than having the parent record behave differently to the child, the Complete / Unsuccessful and Delete confirmation dialogues could have a field that allows the user to set how many requests they wish to apply their action to. This would be defaulted to 1, only available on requests with multiple records. | Still pending but possibly not such an issue now that the list stays in the same row, and the map remains at the same scale.
23 | Parent-Child | Identify Parent request, so if all signs are placed, can tick just Parent. If not all signs placed, can mark each as appropriate. E.g. 2 signs requested, sign at front successful, sign at back not successful. Suggestion: Have child actions in dark grey font colour instead of the usual black. | Please see my comments above | pending
24 | Parent & Child entries | Request for 22 Commercial signs, showing as 22 individual entries in spreadsheet. However for Sponsorship, one entry shown with x Quantity requested. Is it possible to have the latter format for Commercial signs, particularly in the case of Invoicing when one entry is preferred. Invoice Example shown on Invoice tab. | This is a change from the spec, presumably you still need the internal function of treating them as multiple requests, but displayed as a single request with a count? It should be achievable but I will need to take a look to see how much work will be involved. | awaiting feedback
25 | Status labels | Requests Made=Pending Not Invoice, please rename in both areas to Pending. Areas are: - List View, - Status Filter | Not a problem. | Completed
26 | Status Filters Groupings | Completed (Not Invoiced) and Unsuccessful (Not Invoiced) should appear in an additional Not Invoiced filter for Invoicing. | Should be easily achievable, I’ll take a look. | Completed, thank you.
27 | Status labels, Invoicing | Once invoiced, the Completed or Unsuccessful is no longer visible. So from the Agent perspective, when filtering by Unsuccessful, although the results are true, the labels aren't visible. Agent filter options are: Pending, Completed & Unsuccessful. This information is available as part of the CSV export, Columns N & O. Not sure on solution here. | I will take a look to see what can be done to improve this. | Completed
28 | Invoicing | Is it possible to have the file name as a heading in the CSV? See screen snip: | So to clarify, the file name would be included as its own row at the first line of the file? | Yes please.
NEW POINTS
29 | Password reset | Typo on word "request".
30 | List View Filters | Filters reset after making edit to entry. Need to then re-apply filters. Please retain filters selected.
31 | Login error message | When password is incorrect, error message says "User name could not be found". Please re-label to "User name or Password incorrect".
32 | Login set-up | When I create a Branch and set the login and password the new credentials do not work, and I am required to run the Forgot Password function.
33 |  | Complete Column should clear in this new request to now remove this sign. The request has not yet been completed.
34 | Invoicing | Once Invoice is generated, there is no indication in the Invoicing table to show this. Either include the Invoice Status, rather than just Complete/Unsuccessful Status, or have additional column for Date Invoice generated.

## Password Reset Email
Before:
Please change to:

## Invoice
Request Date | Charge Date | Request Description | Address | Status | Cost
2019-11-30 21:22 | 2019-11-30 22:38 | Sales, New Sign, Under Offer | 1 Adversane road, Worthing, BN14 7QH | Completed | 20
2019-11-30 21:22 | 2019-11-30 22:38 | Sales, New Sign, Under Offer | 1 Adversane road, Worthing, BN14 7QH | Completed | 20
2019-11-28 19:21 | 2019-11-29 14:20 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:26 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:01 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:03 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:05 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:05 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-30 19:35 | 2019-11-30 20:34 | Sales, New Sign, Under Offer | 130 Terringes Avenue, Worthing, BN13 1JP | Completed | 20
2019-11-30 19:46 | 2019-11-30 20:09 | Commercial, New Sign, V-Board, To Let | 27a, Chapel road, Worthing, BN11 1EG | Completed | 100
2019-11-30 19:33 | 2019-11-30 20:31 | Letting, New Sign, To Let | 34 Adversane road, Worthing, BN14 7QH | Completed | 20
2019-11-30 20:42 | 2019-11-30 20:46 | Sales, New Sign, For Sale | 36 Charles Avenue, Chichester, PO19 7HF | Completed | 20
2019-11-30 19:40 | 2019-11-30 20:30 | Sales, New Sign, Sold STC | 42 Adversane road, BN14 7QH | Completed | 20
2019-11-30 19:38 | 2019-11-30 20:21 | Sponsorship, New Sign x 15 | Broadwater green, BN14 9DJ | Completed | 300
2019-11-28 19:30 | 2019-11-30 21:00 | Sponsorship, New Sign x 10 | George & Gragon, Worthing, BN14 7NN | Completed | 200