## 2019-12-04
No. | Area | Details | Notes | Update 04-12-2019
7 | List View, Request Date field | This should not update if Ben makes an amendment to the request, as we need to know when the Agent made their Original Request. A removal request is a new request, and as far as I understand, will be a new entry, therefore requiring a new Original Request Date. | The rules I have set up for this are a little more complicated than first explained - and the rules are the same for Ben as for a Branch (in case Ben is handling an emailed request). Essentially if the request was previously completed (or unsuccessful) and the Action has changed or the Action was already of type Change and the Board Type or Sign Type has changed, then it is treated as a new request. Under all other circumstances it is not considered a new request. | When amending address from 11 to 11a, Requested Date stayed the same. When amending quantity from 1 to 2, both Requested Dates showed as different Date/Times, as they should. However Complete Date did not Clear when Request was made to remove the sign using the – button, refer to point 33.
20 | Location Field | Location field allows you to find an existing sponsorship. Essentially, since we do not have the New, Change, etc options for sponsorships, the Location field needs to be always on for modifying a sponsorship request. If you would prefer not to have this it can be removed. |  | Leave for now as it available on other forms too. Can the list populate on part postcodes at all?
22 & 23 | Parent-Child Requests | If agent makes a request for 2 signs, and then decided to delete, they are required to delete twice. Identify Parent request, so if all signs are placed, can tick just Parent. If not all signs placed, can mark each as appropriate. E.g. 2 signs requested, sign at front successful, sign at back not successful. Suggestion: Have child actions in dark grey font colour instead of the usual black. | This ties in with your similar point below about Ben being able to mark multiple signs as completed. You already know my initial thoughts on this but I have been thinking further on the matter. Perhaps rather than having the parent record behave differently to the child, the Complete / Unsuccessful and Delete confirmation dialogues could have a field that allows the user to set how many requests they wish to apply their action to. This would be defaulted to 1, only available on requests with multiple records. | This works OK for the List View but Map view may be more confusing for Users. Has there been any development on you idea in cell D4?
30 | List View Filters | F5 causes the filters to clear. This does not happen with the Map View. The List view filters clear regularly. | We need to decided on best setting. Will the same setting apply to the Agents as well as Ben's view? E.g. Agents@Worthing may prefer that their filters for Worthing to stay on for the list view but not for Map view. Ben would also prefer filters to be retained for the Laist view, and could probably manage with them resetting for the Map view. Is this possible? | Should filters reset upon new login?
33 | Completed Date | Complete Column should clear in this new request to now remove this sign. The request has not yet been completed. | Completed Date did not clear on the the request I made to Remove a sign for Offinton@offington.
MORE POINTS
35 | Agent login set-up | After amending login detail, and accepting changes, the Save button remains bold. Either leave page, or unbold Save button.
36 | Invoicing Filter | We also need to be able to generate one invoice for all Branches, so Branch filter needs to have ALL option as well please.
37 | Invoice Paid | Marking an invoice as paid caused system to hang. Invoice was for £175.00 CJD@Goring. F5 resolved hang but Invoice did not get marked as paid.
38 | List view size | I'm just wondering how long items will stay in the list view for both Stone Sign logins as well as the agent. Requests Invoiced & Paid already appear in new section, so may not be needed in this work area as well. | What is the rule for Agents List views? How long do request stay in the List view?
39 | Sponsorship Entires | We were unable to complete all of the sponsorship request despite ticking as many times as there were forms. Also the first Completeion tick of a sponsorship request populates the Complete Date/Time field but the status is still showing as Pending. | For Signs Categories: Sales, Letting and Commercial, the separate entries work well, so that some can be marked complete while others can be marked unsuccessful. However for Sponsorship where there will be a request for 30 signs it is not feasible to continually mark these are completed. Added to which it shows as one entry of Spnsorship X Quantity.
40 | List View Control | Controls have positioned themsleves om separate rows casuing the rows to be too deep. Better when controls were positioned ina square.
41

## 2019-11-30
No. | Area | Details | Developer Comments | Update 02-12-2019 | Developer Comments 03-12-2019 | Update 04-12-2019
1 | Welcome Page | Lefthand margin needs 0.5cm edge, particularly evident in Mobile view. | Is the intent here to keep the text area the same width as the photo? If so, not so much a case of giving it a 0.5 cm margin but more setting the display area the same width as the image width. Otherwise mobile devices with other screen sizes will still have a potential indent around the picture. | Completed
2 | Welcome Page | Can the Portal link wording be slightly larger? | This is fine, I suggest increasing it to the same size as the Privacy Policy link (increasing from 9pt to 10.5pt font size) | Completed
3 | Moto | Should read in one line as: "Stone Signs: Providing a rock-solid service". I can recall where I saw it two line now, other than the reset email, see point below. | The moto is split on two lines in all the emails. I can change this to match the site. To avoid a large blank area underneath the motto I’ll make the masthead smaller. | Completed
4 | Password reset | Refer to Password Reset Email tab. | I will take a look at the formatting. Clearly this is showing differently between mail clients. | When taken to the password reset screen, please ensure both field are blank, ready for new password to be entered. | This is an annoying aspect of the web browser’s inbuilt password manager, it fills in the password box after the page has been displayed. However, there might be something I can do. | Completed
5 | List View | Wrap all Date/Time columns so Date is on Line 1 and Time is on Line 2, making column width smaller. | Not a problem, and something I had considered myself | Completed
6 | List View | Preferred Column order: 1. Branch 2. Sign 3. Address 4. Status 5. Controls 6. Original Request Date/Time (see point below) 7. Completed Date/Time 8. Updated Date/Time?? | Not a problem to rearrange the columns. Is the Updated column to be the date / time the request was modified (considering your point below). It would require a small change to the database but could be done. | Completed
7 | List View, Request Date field | This should not update if Ben makes an amendment to the request, as we need to know when the Agent made their Original Request. | Not a problem, I can remove the part of the code that updates the date on changes. Plus reading this in conjunction with the previous point, I can add a new Updated field to store this. In the case of an agent making a change, should this follow the same rules as for Ben? For example, one Ben has placed a sign, if the agent then updates the request to a removal, should the requested date or the updated date be changed? | A removal request is a new request, and as far as I understand, will be a new entry, therefore requiring a new Original Request Date. | Noted, I will only update the Original Request date, after completion of the previous request, when it is a change of task. | refer to tab 2019-12-04
10 | Agents & Branches | How do we delete an Agent or Branch? | We hadn’t discussed deletion. If this is a requirement, I suggest we disable them, rather than delete them, for data integrity purposes. | Agreed, will rename to e.g. zzFox & Sons. | I plan to add an Active option for you, so you will not need to put zz at the front. | completed
11 | Agents & Branches, Branch logins | How can I review the Branch logins set-up? We need visibility of this. | To clarfy, you wish for the username field to be visible on the Branch editor? Should this be readonly? Presumably password should still not be available, unless you want to be able to change it? | Yes login to be read only. This means I only get one change to set-up correctly. I suppose worse case I can always rename to "not in use", and start again. | Ok, and if there is a record that desperately needs correcting, you can contact me to change it in the database. | Completed, and any changes to login by the agent are reflected in the admin login as well.
12 | Agents & Branches, Naming convention | Format will be Agent@Location, so no need for Agent in the List view. | Not a problem, I will revert the lists to the single column format. | Agent Name not rquired in List View for Admin login either. | Not a problem, I will remove it. | Completed
13 | Agents & Branches, Sign Pricing label | Please rename Replace to Re-erect in Agent Pricing. | Not a problem. | Completed
14 | Last View | Return to last view, rather than default page. E.g. When viewing list view, do not return to Map view. Also when viewing list and marking as complete, return to same row rather than jump to the top of the list view. | 1) I will look into this. 2) I will see what can be done for this, I have a solution in mind. | Completed, and very pleasing.
15 | Last Map View | Whenever a request is confirmed, the map re-centralises. It is possible to have the map return to last viewed area. Particularly important if marking 6 signs in one areas as complete. Currently User keeps having to re-scale. | I may be limited in what control I have over this, however I will try to find a solution, if one is possible. | Completed, and again, very pleasing. Also agree with your point for resetting the map for Region & Branch filters but please see point 30 below regarding List View filters.
16 | Form Completion, No. of Signs | This should be zero for a blank form and a mandatory field. | Not a problem. | Completed
17 | Form Completion, Save button | Please rename to Submit. | Not a problem, do you want this renamed on admin forms as well, or just the request form? | Completed, not sure any further changes are required. TBC | Will await further comments. | No changes required at this stage.
18 | Form completion | After saving form request, it would feel better to close form and return to higher level screen. This would also work well when saving Agent & Branch information. | So return to the list? That’s not a problem. | Completed
19 | Form Completion | Scenario: Agent requested For Sale, Ben marked as complete, Agent went to change sign but changed from Sales to Letting, and this was allowed to be processed by the app. Sign Categories (Sales, Letting Sponsorship, Commercial) should not be allowed to be amended, once in play. | Ok, I will make this field read only when editing a sign that has been placed. | Completed
20 | Form Completion, Sponsorship Form, Location field | What is the Location field for? | This allows you to find an existing sponsorship. Essentially, since we do not have the New, Change, etc options for sponsorships, the Location field needs to be always on for modifying a sponsorship request. If you would prefer not to have this it can be removed. | I understand the use of the field now. Need to review further. Also used in other re-erect and remove forms. | Will await further comments. | refer to tab 2019-12-04
21 | Pop-up windows | Would it be possible to have the Save and Close near top of window as this is easier with mobile and tablet views. | My initial feeling is that goes against common dialogue design, but perhaps smaller buttons in the top right of the pop-ups would work. I will look in to what can be done with the layout. | Completed and very pleasing.
22 | Requests, deleting requests | If agent makes a request for 2 signs, and then decided to delete, they are required to delete twice. | This ties in with your similar point below about Ben being able to mark multiple signs as completed. You already know my initial thoughts on this but I have been thinking further on the matter. Perhaps rather than having the parent record behave differently to the child, the Complete / Unsuccessful and Delete confirmation dialogues could have a field that allows the user to set how many requests they wish to apply their action to. This would be defaulted to 1, only available on requests with multiple records. | Still pending but possibly not such an issue now that the list stays in the same row, and the map remains at the same scale. |  | refer to tab 2019-12-04
23 | Parent-Child | Identify Parent request, so if all signs are placed, can tick just Parent. If not all signs placed, can mark each as appropriate. E.g. 2 signs requested, sign at front successful, sign at back not successful. Suggestion: Have child actions in dark grey font colour instead of the usual black. | Please see my comments above | pending |  | Merge with No.22
24 | Parent & Child entries | Request for 22 Commercial signs, showing as 22 individual entries in spreadsheet. However for Sponsorship, one entry shown with x Quantity requested. Is it possible to have the latter format for Commercial signs, particularly in the case of Invoicing when one entry is preferred. Invoice Example shown on Invoice tab. | This is a change from the spec, presumably you still need the internal function of treating them as multiple requests, but displayed as a single request with a count? It should be achievable but I will need to take a look to see how much work will be involved. | awaiting feedback |  | Completed
25 | Status labels | Requests Made=Pending Not Invoice, please rename in both areas to Pending. Areas are: - List View, - Status Filter | Not a problem. | Completed
26 | Status Filters Groupings | Completed (Not Invoiced) and Unsuccessful (Not Invoiced) should appear in an additional Not Invoiced filter for Invoicing. | Should be easily achievable, I’ll take a look. | Completed, thank you.
27 | Status labels, Invoicing | Once invoiced, the Completed or Unsuccessful is no longer visible. So from the Agent perspective, when filtering by Unsuccessful, although the results are true, the labels aren't visible. Agent filter options are: Pending, Completed & Unsuccessful. This information is available as part of the CSV export, Columns N & O. Not sure on solution here. | I will take a look to see what can be done to improve this. | Completed
28 | Invoicing | Is it possible to have the file name as a heading in the CSV? See screen snip: | So to clarify, the file name would be included as its own row at the first line of the file? | Yes please. | Ok, not a problem. | completed
29 | Password reset | Typo on word "request". |  |  | I can’t believe I missed that! Will correct it. | completed
30 | List View Filters | Filters reset after making edit to entry. Need to then re-apply filters. Please retain filters selected. |  |  | Ok, there are two possible ways of doing this, the less tidy way is to pass the filters to the next page and then pass them back again. The cleaner way would be to store the current filters (much like we do with the selected Region on the map view) however that will mean the filters will always persist when leaving and returning to the list or map views. Unless you state the second method is undesirable, this is the approach I will take. | refer to tab 2019-12-04
31 | Login error message | When password is incorrect, error message says "User name could not be found". Please re-label to "User name or Password incorrect". |  |  | Not a problem. | completed
32 | Login set-up | When I create a Branch and set the login and password the new credentials do not work, and I am required to run the Forgot Password function. |  |  | I will look into this. | possible user error
33 | Completed Date | Complete Column should clear in this new request to now remove this sign. The request has not yet been completed. |  |  | Shouldn’t be a problem. | refer to tab 2019-12-04
34 | Invoicing | Once Invoice is generated, there is no indication in the Invoicing table to show this. Either include the Invoice Status, rather than just Complete/Unsuccessful Status, or have additional column for Date Invoice generated. |  |  | I’m a little puzzled, when an Invoice is generated, the records should disappear from the list, as it is a list of uninvoiced records (which is why the invoice status isn’t shown). Can you confirm if the list is not being cleared? | Web page did not refresh in this instance, and I was able click again on "Generate Invoice", not that anything happened.

## Password Reset Email
Before:
Please change to:

## Invoice
Request Date | Charge Date | Request Description | Address | Status | Cost
2019-11-30 21:22 | 2019-11-30 22:38 | Sales, New Sign, Under Offer | 1 Adversane road, Worthing, BN14 7QH | Completed | 20
2019-11-30 21:22 | 2019-11-30 22:38 | Sales, New Sign, Under Offer | 1 Adversane road, Worthing, BN14 7QH | Completed | 20
2019-11-28 19:21 | 2019-11-29 14:20 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:26 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-29 14:27 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:01 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:03 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:05 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:05 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:06 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-28 19:21 | 2019-11-30 21:07 | Commercial, New Sign, S-Board, Coming Soon | 113 Terringes AVenue, BN13 1JN | Completed | 50
2019-11-30 19:35 | 2019-11-30 20:34 | Sales, New Sign, Under Offer | 130 Terringes Avenue, Worthing, BN13 1JP | Completed | 20
2019-11-30 19:46 | 2019-11-30 20:09 | Commercial, New Sign, V-Board, To Let | 27a, Chapel road, Worthing, BN11 1EG | Completed | 100
2019-11-30 19:33 | 2019-11-30 20:31 | Letting, New Sign, To Let | 34 Adversane road, Worthing, BN14 7QH | Completed | 20
2019-11-30 20:42 | 2019-11-30 20:46 | Sales, New Sign, For Sale | 36 Charles Avenue, Chichester, PO19 7HF | Completed | 20
2019-11-30 19:40 | 2019-11-30 20:30 | Sales, New Sign, Sold STC | 42 Adversane road, BN14 7QH | Completed | 20
2019-11-30 19:38 | 2019-11-30 20:21 | Sponsorship, New Sign x 15 | Broadwater green, BN14 9DJ | Completed | 300
2019-11-28 19:30 | 2019-11-30 21:00 | Sponsorship, New Sign x 10 | George & Gragon, Worthing, BN14 7NN | Completed | 200