## TestNotes
Item No. | Topic | Portal Area | Item | Comments | Further Information | Dev Notes 29/03/2021 | Dev Status 31/03/2021 | Hannah April 2021 |  | Scott 13/04/21 + HD 13-04-2021
1 | Invoice Recipient | Agents | Invoice Recipient fields | When Invoice Recipient Send To = Branches, in the Agent record, then Invoice Recipient fields in the Agent record should be non-modifiable, as they are not required here. - Invoice Recipient Name, - Invoice Recipient Email, - Invoice Recipient CC |  | I had left this as available, so as to provide a fall back contact for when one hasn’t been set up in a relevant Branch. But yes, we can make the fields non editable. | Done. I've had to make the Default Name and Default Email fields non-mandatory for Branch types. | Discovery of redundant fields in Agent record, please refer to Item 26, in place of this one. |  | Comments in 26
2 | Invoice Recipient | Branches | Invoice Recipient fields | When Invoice Recipient Send To = Branches, in the Agent record, then Invoice Recipient fields in the Branches records should be Mandatory. |  | Ok, but please note any already created Branches will be left with unpopulated mandatory fields. | Done. | complete |  | That's fine, will make it mandatory
3 | Invoice Recipient | Agents | Invoice Recipient fields | When Invoice Recipient Send To = Main Office, in the Agent record, then how do we check that one of the Branches has been set to Main Office? Perhaps this check can be made at the point of raising an invoice? E.g. "Invoice Recipient is Main Office but the Main Office has not been set". Also issue with invoice reference number when the Main Office is not set-up, i.e. shows as "000". |  | Ok, yes we could perform this check when raising the Invoice, that would then prevent the situation described with the reference number of “000”. | Done. | complete
4 | Invoice Recipient | Branches | Invoice Recipient fields | When Invoice Recipient Send To = Main Office in the Agent record and more than one Branch is set to Main Office, the last updated Branch will keep the Main Office setting, and the earlier Branch will revert to Branch. Please can we have a pop-up informing us of this update. |  | Ok. | Done. | complete |  | Will look at adding this to settings.
5 | Invoice Recipient | Branches | Branch Code and Invoices To Columns | Please include on front view for Branches. NB: The Agent Column is not necessary required, if you need the real estate. |  | Not sure I understand, Code and Invoice Recipient are already on the Branches list? | N/A | n/a |  | The Invoice Recipient fields in Agent provide a fallback, although the Recipient fields are mandatory on Branches where the Agent is set to Send To Branch, when the Agent is set to Send To Main Office then they aren't mandatory. The Validation check performed when raising an invoice also takes into account this fallback address. However, if you want, I could make the Recipient fields for Main Offices mandatory, which would then make the Agent level ones redundant. As it stands, if the fallback Recipient is used, then the Agent's Address is also used. If we implement the change I described above, then we could also remove the Agent's Address fields. Yes, I can change the label to "If Main Office" and clear it when Send To is set to Branches. Should this be a cosmetic hiding of the Main Branch (leaving the status Main Branch on the related Branch record - it would have no effect being left set) or do you want me to reset the Branch record when the Agent record is saved?
6 | Auto Invoice | Invoicing | Incorrect invoice block | When Invoice Recipient Send To = Branches, in the Agent record, when the invoice is raised as per Agent Filter, and no Branch is set, a warning message should prevent the invoice from being raised. |  | Ok. | Done. | complete |  | Ok, this can be done.
7 | Auto Invoice | PDF Invoice | Invoice Number | With reference to the above Main Office and Branch set-ups, if the set-up is incorrect, the Branch code used in the invoice number on the PDF is "000". | (also mention in Item no. 3 above) | The resolution to points 3 and 6 should prevent this. | Done. | complete |  | When an Agent is set to Send To Branch, all Branches are treated as Branch (a status of Main Office is ignored): I can add a validation at the point of raising an Invoice, but it shouldn't be neccessary. Do you still want me to add this check?
8 | Auto Invoice | Invoicing & Payments | Raising an invoice, and making amendments. | The raising of an invoice involves the following steps: 1. Invoicing -> Filter -> Generate CSV invoice. 2. Payments -> download (if required) 3. Payments - Send Invoice. There is currently no opportunity to make amendments because once the CSV has been generated, the items then move to Payments. | Needs further discussion, email sent to Scott on 26/03/2021 explaining situation. | Will implement Draft Invoices as discussed. | Done. | complete |  | I've found the cause of this and can easily fix it.
9 | Auto Invoice | PDF Invoice | Re-issuing invoices with corrections | In the event the invoice was incorrect, as raised by the Agent, we need facility to make correction and re-issue invoice. | Appreciate this is not included in initial spec. To discuss further. | When adding the draft functionality in point 8, we could expand the editing of Invoice Lines to the Payments list as well. | Done. | complete |  | Will need to investigate further, but the first error message appears to be related to the Invoice Number having a suffix and RFC error appears to be related to an invoice not having a Branch when set to Branch level invoicing. For example the top entry in the Payments list is for Fox & Sons with no Branch but Fox & Sons is set to Send To Branch. Do you previously have this set to Send To Main Office, generate the Invocie, and then change it to Send To Branch? That's the only way I can see this situation arrising? This might be a case for keeping the fallback recipient, and making it mandatory.
10 | Auto Invoice | Payments | Send invoice icon | Need a decision box to ask to confirm sending of invoice. "Send Invoice V1 Y/N" |  | Ok. | Done. | complete |  | Should the old invoice record remain as well, essentially creating two invoices, or should the original invoice simply be assigned the new reference? Regarding your question, is that enquiring how I will identify when to generate the new suffix? I would need to update the invoice record to to store a flag indicating that there has been a change that requires a new suffix, and then remove that flag when the suffix has been generated?
11 | Auto Invoice | Payments | Send invoice icon for PAID Invoices | Can this icon be removed or disabled for Paid invoices. The ability to download the PDF is still useful. |  | Ok. | Done. | complete |  | Ok, this can be set to disabled and blank when no Agent set, althoug as you mentioned it has no effect when there isn't an Agent. The 13 pins in the example are Completed requested, if you have emulation turned off you can see them by changing the Status to Placed.
12 | Auto Invoice | Settings & PDF Invoices | Changes to VAT Rates | If an invoice is re-issued, and the VAT amount has changed, then the invoice shows the VAT label at the new rate, but still calculates at the old rate. Example screen print, first invoice generated when VAT was 50%, re-issuing after the VAT has changed to 20% shows the VAT label to be the new rate of 20%, but the calculation at the old rate of 50%. The values is correct, as this should not change when re-issuing invoices but the label is wrong. |  | Ok, will need to store the VAT Rate against the Invoice record. I’ll set any records already in the system to 20%. | Done. | complete |  | I'll check the reminders sent count. As for the error message, please refer to 30.
13 | Auto Invoice | PDF Invoice | Invoice Payment Ref | Please used shortened version of invoice for Payment Ref. owing to some banks having limit space for reference numbers. E.g. ABC123-YY-MM |  | Ok. | Done. | complete
14 | Auto Invoice | Invoice email | Wording in email | Change to wording owing to current wording not being suitable for re-issuing of invoices. such as if the email is sent as a reminder, then the wording is incorrect. Perhaps we can change to: "Please find attached the invoice for work carried out in Month YYYY." "Payment information is detailed below, please use the specified Payment Ref." | Incidentally, how is month generated? Can it be based on the Complete Date month in the majority of request? | Ok. | Done. | complete (Email sent to Scott 07-04-2021 with example of invoice email wording.)
15 | Auto Invoice | PDF Invoice | Font | You mentioned that font choices were limited. Ideal is Calibri Light size 11 if possible. Can the "Many Thanks" be italized? |  | I believe I might be able to get Calibri Light to work. I won’t know for sure until I test it on the server. Italics is not a problem. | Unfortunately, the font is limited to whatever is installed on the server (not something I have any control over - I have cPanel access not root access), I tried Calibri Light but it wasn't available (I don't have a list of what is available - I have to try a font to see if it works). I have, however, set "Many Thanks" to italic. | complete
16 | Auto Invoice | Payments | Reminder | Not required as the re-issuing of the invoice will be carried out instead. | already removed. | The reminder button is still there, will remove it. | Done. | complete
17 | Accountant Data | Payments | New filter option | Additional filter item require for Status, to include All Invoices. |  | Ok. | Done. | complete
18 | Accountant Data | Payments | Accountant data in CSV format | In you email you said: "You can also use this date range filter to return details about invoices from before the normal 3 month historical limit." I'm hoping there is more than three month's data, please confirm? Ideal amount is 12 months. |  | All records are retained in the database. To prevent the Invoices list from getting too long (for display purposes), it currently only shows the last 3 month’s of data (I think we discussed the range limit during phase 1 development and settled on 3 months). The new date range filter allows you to access the older data. If you need to access 12 months of data now (prior to going live with phase 2), let me know and I’ll change the default filter to 12 months in the Live system. | Nothing to change. | n/a
19 | New Fields | Agents | Agent Code field label | Please rename to "Agent Code" |  | Ok. | Done. | complete
20 | New Fields | Branches | Branch Code Field Label & location | Please relocate to top of screen & rename "Branch Code", similar to Agent arrangement, refer to screen print. |  | Ok. | Done. | complete. (Email sent to Scott 07-04-2021 Record fields updated, as per image.)
21 | New Fields | Branches | Branch Type location field | Please relocate to top of screen, under Branch Code. |  | Ok. | Done. | complete
22 | Columns | Branches | Branch Type Column | Please display as an addition column on front screen of Branches. |  | Ok. | Done. | complete
23 | Columns | Payments | Sort Order | Please sort in reverse Invoice Date order by default. |  | Ok. | Done. | complete
24 | Worklist CSV Export | List View | Export CSV in Postcode Order | Sort order appears to be working perfectly. Only issue is that when filtered by region, cannot enter a starting postcode in Worthing, i.e. Ben's house. Also unhelpful error message displayed. If Postcode is not valid, CSV will open in sort order alpha-numeric postcode. Is it possible to carry out Postcode validation, rather than provide incorrect sort order? |  | I have a solution to the 500 error. Will look at validating the postcode. | Done. | OK for entering Worthing postcode on a Shoreham to Seaford filter, thank you. Also postcode validation working well... However, if Postcode is not entered, the distance ordering does not work, and the Postcodes are sorted alphanumeric which we don't want. Without Postcode please prevent CSV from loading, i.e. Make Postcode mandatory. |  | That's fine, will make it mandatory
NEW ITEMS
25 | Business Details | Settings | Address Fields | There has been a change in business address, would it be best to have Business Address fields provided on the Settings to merge into the invoices? If not, the updated address is: 314a Goring Road, Worthing, West Sussex, BN12 4PE | [5 empty] | Will look at adding this to settings.
26 | Agent Fields | Agents | Redundant fields. | Are the Invoice Recipient Fields redundant in the Agent record? We are mainly concerned with if we are sending to Main Office or to Per Branch. The system has a check in place at point of raising invoices to check for Main Office, and the details in the Main Office Branch record overwrite anything written in the Agent record. Also the Head Office address may not be required. |  |  |  | if you agree that the mention fields are redundant, then suggested layout.-----> Where it current says Main Office as a field label, please can this say "if Main Office". Also if the Agent's Invoice Sent To=Branches, is it possible to clear the "if Main Office" field? |  | The Invoice Recipient fields in Agent provide a fallback, although the Recipient fields are mandatory on Branches where the Agent is set to Send To Branch, when the Agent is set to Send To Main Office then they aren't mandatory. The Validation check performed when raising an invoice also takes into account this fallback address. However, if you want, I could make the Recipient fields for Main Offices mandatory, which would then make the Agent level ones redundant. As it stands, if the fallback Recipient is used, then the Agent's Address is also used. If we implement the change I described above, then we could also remove the Agent's Address fields. Yes, I can change the label to "If Main Office" and clear it when Send To is set to Branches. Should this be a cosmetic hiding of the Main Branch (leaving the status Main Branch on the related Branch record - it would have no effect being left set) or do you want me to reset the Branch record when the Agent record is saved? HD: these changes have come out of attempting to get my head round the set-up, and so for the sake of streamlining, please remove the redundant fields, and hide the "Main Office" setting if Invoice Send To=Branches in the Agent record. Yes please make fields mandatory as you have described above. The fall back fields are not required owing to the recently added validation.
27 | Invoice Recipient | Branches | Invoice Recipient fields | When Invoice Recipient Send To = Main Office in the Agent record, ideally, for any Branches showing as "Branch" the Invoice Recipient fields should be non-modifiable. E.g. Bacon & Co with one main office and two branches. | [5 empty] | Ok, this can be done.
28 | Invoice Send To | Agents & Branches | Send To Combinations | Combination set-ups that are correct: - Agents=Invoice Sent To Main Office, Branch=Invoice Send To Main Office (and only on Main Office permitted by the system). - Agents=Invoice Send To Branches, Branch=Invoice Send To Branches Combination set-up that are not permitted due to system validation: - Agents=Invoice Sent To Main Office, Branch=Invoice Send To Branch "Main Office Not Defined" at point of raising invoice. Combination currently not checked: - Agents=Invoice Send To Branch, Branch=Invoice Send To Main Office We currently have a "Branch Level" check at the point of raising an invoice, please can we also have a validation to ensure if Agent=Send Invoice to Branches, then all the Branches=Send Invoice to Branches. | [5 empty] | When an Agent is set to Send To Branch, all Branches are treated as Branch (a status of Main Office is ignored): I can add a validation at the point of raising an Invoice, but it shouldn't be necessary. Do you still want me to add this check? HD: OK this can be left as it is as the setting in the Agent record is the control over how invoices are raised.
29 | VAT Label | PDF Invoice | VAT Label showing as 0% | VAT label showing as 0% on invoices raised for Houses4Sale issued on a per Branch basis. All invoices VAT label showing 0% although calculated at 20%. Sent invoices also showing VAT as 0%. When set-up is "Send To Main Office", (two branches, one the main one) VAT labelled shows as 20% as expected. Also tested with one branch (Rachel Lettings) set-up as Main Office, VAT showed as 20%, however when tested with the same one-branch set-up but using the Branches label in both Agent and Branch, VAT showed as 0%. | [5 empty] | I've found the cause of this and can easily fix it.
30 |  | Draft Invoices | Send Invoice Control Icon | Unexpected error message displayed when sending out invoice, refer to screen print. Invoice did not send but invoice was moved to Payment section. Got this error as a result of: 1) raising an invoice for Drafts, 2) making amendment from Draft Invoices. 3) Sending invoice via envelope control. Resending the invoice from Payments section resulted in same error message. Also get similar message in Payment section, filter by Hannah Dilley Letting and attempted to resend any unpaid invoice from here. |  |  |  |  | Another example of error message received when attempting to resend invoices from the Payment section. | Will need to investigate further, but the first error message appears to be related to the Invoice Number having a suffix and RFC error appears to be related to an invoice not having a Branch when set to Branch level invoicing. For example the top entry in the Payments list is for Fox & Sons with no Branch but Fox & Sons is set to Send To Branch. Do you previously have this set to Send To Main Office, generate the Invoice, and then change it to Send To Branch? That's the only way I can see this situation arising? This might be a case for keeping the fallback recipient, and making it mandatory. HD: The data has been heavily manipulated and so it is quite possible that I have chopped and changed between Send Invoice To settings. I have set up a new Agent "A New Agent", and attempted to recreate the issue but did not succeed, so all is good. However, what happens then in the event the set-up changes in real life? For example A New Agent uses the Main Office to send invoices, however as the branches expand, the Agent chooses to split the invoices on a per Branch basis. They have an unpaid invoice from the old set-up, does this mean we won't be able to resend it?
31 | Invoice Numbers | PDF Invoice | Generation of invoice numbers. | 1) When an invoice is first raised, the month shows as 04 - this is correct 2) When invoice is amended as a draft, the month shows as 04 - this is correct 3) When the invoice is re-issued with no correction made, the month shows as 04 - this is correct. 4) When invoice is amended after sending (owing to complaint from Agent), the month still shows as 04 but this is now a revised invoice and should show the suffix "a". - this is not correct. NOTE: we only issue one invoice per month unless a correction is required. |  |  |  | Resending invoice following an amendment should have the suffix of a, b, c, etc. But how can you tell if it's a resend or a revision? |  | Should the old invoice record remain as well, essentially creating two invoices, or should the original invoice simply be assigned the new reference? Regarding your question, is that enquiring how I will identify when to generate the new suffix? I would need to update the invoice record to to store a flag indicating that there has been a change that requires a new suffix, and then remove that flag when the suffix has been generated? HD: We don't really need the original invoice, but the re-issue will need the suffix. This is only in the event that the invoice has already reached the Agent, and does not apply to Draft Invoices.
32 | Emulate tick box | List View |  | Emulate button should be empty & non-mod when Agent is not selected. Although I'm not sure if the function of this tick box is effective: when set for Houses4Sales @Arundel, checking the Emulate tick box caused all map pins to disappear but unchecking showed 13 pins which matched the actual login for Houses4Sale@arundel (password: hannah11), FYI. | [5 empty] | Ok, this can be set to disabled and blank when no Agent set, although as you mentioned it has no effect when there isn't an Agent. The 13 pins in the example are Completed requested, if you have emulation turned off you can see them by changing the Status to Placed. HD: Yes I agree that map pins (x13) can be seen without emulation (and Status is set to "Placed"). Why then do they disappear when I check the Emulate tick box but reappear hen I change the Status to "Requests"? If you think this is not really an issue, then that's fine too.
33 | Accountant Data | Payments | Accountant data in CSV format | Column I - Reminders Sent, I'm not convinced this is actually providing a count, unable to check today owing to issue with resending of invoices, refer to screen print. | [5 empty] | I'll check the reminders sent count. As for the error message, please refer to 30.

## As per Spec
No. | Item | Area | Details | Tester Comments
1 | New fields | Agents | Invoice Agent Code, (3 letter code) Invoice Recipient Office, (Options: Invoice Main Office or Invoice Branches) Invoice Recipient (already exists) Invoice Recipient CC, (new) New Post fee, Disposal of Flag Tops fee. Will also contain Main Office / Branch preferecne for invoicing. | Refer to TestNotes
2 | New Fields | Branches | Branch Type, (Options: Main Office or Branch) Invoice Branch Code, (3 letter code) The following are only applicable if the Branch is the Main Office or Invoiced per branch: - Invoice Recipient Name, - Invoice Recipient Email, - Invoice Recipient CC Will also contain Invoice Recipient Office preference. | Refer to TestNotes
3 | Columns | Agents | Sign Placed, Unsuccessful, Changed, Re-erected, and Removed. New Post, Disposal of Flag Tops Agent Code field, Invoice Recipient | OK
4 | Columns | Branches | current branch Email, Branch Code, Invoice Recipient fields | OK
5 | Columns | Payments | Invoice Number, VAT, Gross Charge, Payment Received Date | OK
6 | Additional info | Map View | Add requested Date. | OK
7 | Filters | Map View List View Invoice List | New filter option to include: Estate Agent Branch, Address (string search) Postcode, (string search) Requested Date Range, (inclusive of start and end dates) Completed Date Range (inclusive of start and end dates). | OK
8 | Viewing other Agents Portal | Map View List View Invoice List | The Agent & Branch filter is to activate a checkbox for Emulate Agent, that when checked shows the same results that the Agent would see. | OK
9 | Invoice CSV & Filter | Payments | New filter option: Date Paymenet received (inclusive of start and end dates). To enable export of Payments received for a data range for the purpose of VAT information. CSV columns to include: - Invoice Number, - VAT, - Gross Charge - Date Payment Recieved | OK
10 | Export CSV in Postcode Order | List View | When generating a CSV export of the List View a dialogue box will be displayed offering the chance to sort by distance. | Refer to TestNotes
11 | Additional Items | Ad hoc Request (Admin users only) | Items will be automatically marked as complete, and will not generate a pin drop. Additional Items include: New Posts, Change Over, Disposal of Flag Tops, other Additional Items. | OK
12 | Quantity Field | Invoice View | Additional field to change the quantitiy in the event more posts were erected or removed. Similar to Price change function. | OK
13 | Quick Search | All Pop-up Lists | Enable list to jump to Agent will starrting letter that is typed. | OK
14 | Stone Sign Bank Details | Automated Invoicing | New fields to include: - Payment Account Name, - Sort Code, - Account Number. | OK
15 | PDF Invoices | Automated Invoicing | A facility to export invoices to a PDF file will be added. The current “Download CSV file” button will be replaced with a “Download” button that will display a menu to choose between the existing “CSV export” option and a new “PDF download” option. The PDF file will be designed to as closely match the existing Stone Signs i nvoice design as possible, and i nclude payment details along with instructions to use the Invoice number as the payment reference. The recipient address and contact name, will be governed by the Branch’s Branch Type field and the Agent’s Invoice Recipient Office field. The PDF file will be generated ‘ on the fly’ from the information stored in the database, as opposed to being saved to the file store. The downloaded PDF file will use the invoice number as the file name. The Payments list will add a new button called “Send Invoice”. When clicked an email will be sent to either the Branch, Main Office or Agency (depending on the configuration of Invoice Recipients i n the Agent & Branch records) with a PDF i nvoice attached. The emailed i nvoice will be generated to the specifications mentioned above. | Refer to TestNotes

## Original List
No. | Item | Area | Details
1 | Additional Columns | Payments View | Show additional columns for VAT and Gross in Payments View.
2 | Additional Columns | Agent View | Display all non-commercial Fee settings as additional Columns on Agent list, plus two new additional values ones: New Post & Disposal of Old Flag. Screen shown prior to accessing Agent record.
3 | Additional Columns - NEEDS REVIEW | Branch View | Display email address as additional column on screen shown prior to accessing Branch record. Other columns likely to be required as a result of the Invoicing development such as Branch Invoice Code, etc.
4 | Additional Filters | List View Invoice View & Map View | Additional filter options to include: - Estate Branch, - Address String, - Postcode, - Request Date Range - Completed Date Range.
5 | Date Requested | Map View | As part of pop-up linked to a pin drop, please include "Date Requested".
6 | Postcode Ordering | Export to CSV | As part of the preparation worksheet for other staff, the job worksheet is exported to Excel where the addresses are sorted into execution order. This is currently being done by "Town" but town is not always completed correctly. We would like to use Postcode to set the execution order, and wonder if it is possible to export the worksheet in execution order starting with closest to Worthing, and ending at Seaford, and likewise, starting at Worthing and ending at Selsey.
7 | Quick Find | All lists (& filter lists) containing Agent name. | When opening a list (such as agents in Ad hoc Request) allow quick find by entering starting letter of Agent, e.g. Press M to jump to Michael Jones.
8 | Additional Field for Quantity. | Invoicing View | As part of the edit function in the Invoicing View, allow the quantity to be changed in the event that additional signs were erected or removed.
9 | "Additional Items" Request Option | Ad hoc Request | There are times when additional items such as Posts need to be added to the Portal so that they are included as part of the invoice. Currently we use the sign remove option to record this. Using removal also means that there is no sign placed in the Map or List view. Can we add additional fields to the Ad hoc Request Form? - By adding the option "additional Item" to the Sign Category field, this can allow input of Quantity, we will add "Post" to Address Line 1, and normally we add the Branch's postcode in the Postcode field. We would also need an additional field to set the price. An Additional items should not add any pin drops to the Map or List Views, and should automatically be registered as "complete". In the Invoice, this should be shown as "additional item", all other columns can remain the same.
10 | Automated Invoicing | Invoicing | To be discussed as part of meeting, points to note: Please refer to tab Invoicing Data to support points 1, 2 & 3 below. 1) Most Branches have an invoice issued per login (e.g. one for Sales one for letting, and one per Branch). Some agents however amalgamate all Branches. 2) We will need email address field to reflect Agent's choice of receiving their invoices. 3) We also need fields to hold the invoice numbering format er Branch. Ben is looking to use Xero accounting software to log VAT (as advised by his Accountant), he is looking to link this with the Portal if at all possible? Other options to consider is using the VAT and Net values available in the system and providing some sort of export report...
11 | Agent's View |  | View of Agent's List View from the Admin Login